## Construction SOW Template
CONSTRUCTA FAMILY BUILDING LLC
Mayson Reed
5850 West Road, Plumlee, VA 58220
PROJECT ADDRESS: 202 Building Street, Fortworth, NY 21454
CONTRACTOR: FAMILY HOUSES INC.
Job Summary: |  | Single Family Home
Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Maecenas porttitor congue massa. Fusce posuere, magna sed pulvinar ultricies, purus lectus malesuada libero, sit amet commodo magna eros quis urna. Nunc viverra imperdiet enim. Fusce est. Vivamus a tellus. Pellentesque habitant morbi tristique senectus et netus et malesuada fames ac turpis egestas. Proin pharetra nonummy pede. Mauris et orci. Aenean nec lorem.
| Building Site Preparation & Pouring the Foundation |  | Duration
ACTION #1 | Clear rocks, debris, and trees |  | 3d
| Level the site prior to pouring the foundation |  | 2d
| Pouring the foundation |  | 1d
| Inspector examinations |  | 1d
| Framing, Plumbing, Electrical & HVAC |  | Duration
ACTION #2 | Install walls, windows, and doors, as well as the floor and roof systems |  | 10d
| Install plumbing, HVAC, and electrical |  | 10d
| Inspector to approve pipes, electrical wiring, and heating and cooling ducts |  | 1d
| Adding Insulation and Drywall |  | Duration
ACTION #3 | Insulate exterior walls, and areas around a basement, crawl spaces, and attic |  | 5d
| Hang drywall and cover any raised surfaces |  | 4d
| Lorem Ipsum |  | 3d
| Interior & Exterior Finishes |  | Duration
ACTION #4 | Finish fireplace, mantle, internal doors and window sills, and decorative trim |  | 11d
| Work on driveways, walkways, and patios |  | 7d
| Installing Fixtures & Flooring |  | Duration
ACTION #5 | Install hardwood flooring |  | 3d
| Install light switches and faucets |  | 6d
| Inspection |  | Duration
ACTION #6 | The final inspection by a building code official |  | 3d
| Final Walkthrough |  | Duration
ACTION #7 | Show the new home’s amenities and cover owner's responsibilities under warranty |  | 1d
SCOPE OF WORK

## ©
© TemplateLab.com